## Sheet1
Day | Time | Location | What we did | What will be done next time | Did we accomplish what we were supposed to?
2018-02-21 | 9-10 am | LEEP2 | Set-up repository, worked on being | Dividing responsibilities, Planning, Potentially | N/A
|  |  | able to run original program | start fixing original program requirements
2018-02-23 | 9-10 am | LEEP2 | Updated backlog and assigned task | Hopefully assigned tasks done by Monday | Yes
2018-02-25 | 7-9 pm | LEEP2 | Created classes and objects to help | Finalize new classes and start fixing bugs | No
fix the problems of original program
2018-02-26 | 9-10 am | LEEP2 | Discussed how to implement new | Find a way to display to console | Yes
requirements and UI
2018-02-26 | 3-5 pm | Eaton | Got the sln file to finally work and | Read/Write, Other stuff | Kind of?
made changes to Event and Task
2018-03-02 | 10:30 | Anshutz | Worked on UI/ fixed some minor errors | More UI | Yes